## Query-Log
S.NO | FDD Version | Phase/Model | Query | Offshore Comment | Onshore Comment | Query by | Query Raised on | Query Addressed on | Assigned to | Status
1 | 1 | Initial | What are the required form validation constraints? (Like length of Name, Email and Phone Number) | for Name, Email and Phone number. |  | Vijay Muccharla | 25th-July-20 |  | Ashok C | Open-in-progress
3 | 1 | Initial | While editing, if Alex wants to cancel editing? | Do we add a Reset/Cancel button? |  | Vijay Muccharla | 25th-July-20 |  | Ashok C | Open-in-progress
4 | 1 | Initial | Only one phone number can be added for each contact? | What if there is a Secondary phone number? |  | Vijay Muccharla | 25th-July-20 |  | Ashok C | Open-in-progress
5 | 1 | Initial | How many 'Contacts' are to be displayed in 'AllContacts' page? | No. of Contacts to view in 'AllContacts' page |  | Vijay Muccharla | 25th-July-20 |  | Ashok C | Open-in-progress
6 | 1 | Initial | Duplicate Email and Phone allowed? | Same Email, Phone number cannot be used for multiple Contacts? |  | Vijay Muccharla | 25th-July-20 |  | Ashok C | Open-in-progress
7 | 1 | Initial | Server /Client side validations? |  | Server side validations if Client side validations are not done, otherwise vice-versa. | Vijay Muccharla | 25th-July-20 |  | Ashok C | Closed
8